## Лист1
Статус | № п/п | Код объекта | Проект № / Project No.: | Вид работ | Type of work | Бетонирование | RFI | Дата составления | Дата освидетельствования | Время освидетельствования | Время составления
|  | 00UTH | AKU.1309.00UTH.0.KZ.LB0003 | После бетонирования каналов KLm1(4 шт) и KLm2(1 шт) с отм. -1,000 до отм. +0,000 и фундамента под оборудование Fom2(5 шт) с отм. -1000 до отм. +0,670 и фундамента под оборудование Fom1(6 шт) с отм. -0,700 до отм. +0,000 в осях E/7-12 | After concreting channels KLm1 (4 pcs) and KLm2 (1 pc) with elev. -1,000 to el. +0.000 and foundation for equipment Fom2 (5 pcs) with elev. -1000 to el. +0.670 and foundation for equipment Fom1 (6 pcs) with elev. -0.700 to el. +0.000 in axes E/7-12 | + | ЗНО-62415 | 2023-07-11 | 2023-07-12 | 14:00 | 9:37
|  | 00UTH | AKU.1309.00UTH.0.KZ.LB0003 | Установка закладных изделий стальных изделий колонны в осях Е/11 на отм. -1,700 до +0,000 согласно исполнительной схеме AKU.1309.00UTH.0.KZ.LB0003-SINTEK-ABD | Installation of embedded products of steel products of the column in the axes E / 11 at el. -1.700 to +0.000 according to executive scheme AKU.1309.00UTH.0.KZ.LB0003-SINTEK-ABD | + | ЗНО-62416 | 2023-07-11 | 2023-07-12 | 14:00 | 9:41
|  | 00UKU | AKU.0179.00UKU.0.KZ.TB0010 | Подготовка поверхности перед ремонтом колонн Cn4-D, Cn5-D, Cn5/1-D ,Cn6-D, Cn10-D, Cn11-D, Cn12-D, Cn13-D, Cn14-D, Cn15-D в осях D/4-15 с отм. +7,700 до отм. +10,500 | Surface preparation before repair of columns Cn4-D, Cn5-D, Cn5 / 1-D , Cn6-D, Cn10-D, Cn11-D, Cn12-D, Cn13-D, Cn14-D, Cn15-D in the axes D / 4-15 from elev. +7,700 to el. +10,500 |  | ЗНО-62417 | 2023-07-11 | 2023-07-12 | 15:00 | 9:56
|  | 00UKU | AKU.0179.00UKU.0.KZ.TB0010 | Подготовка поверхности перед ремонтом стен в осях D/7-9 с отм. +7,700 до отм. +11,100 | Surface preparation before repairing walls in axes D / 7-9 with elev. +7,700 to el. +11,100 |  | ЗНО-62418 | 2023-07-11 | 2023-07-12 | 15:00 | 9:59
|  | 02UEK | AKU.1309.02UEK.0.KZ.LB0001 | После бетонирования бетонной подготовки фундамента склада масел 02UEK с отм. -1,650 до отм. -1,550 | After concreting the concrete preparation of the foundation of the oil storage 02UEK with elev. -1,650 to el. -1,550 |  | ЗНО-63434 | 2023-07-11 | 2023-07-12 | 14:30 | 13:21
|  | 02UEK | AKU.1309.02UEK.0.KZ.LB0001 | Устройство опалубки фундамента склада масел 02UEK с отм. -1,680 до отм. -1,650 согласно исполнительной схеме AKU.1309.02UEK.0.KZ.LB0001- SİNTEK-ABD | Foundation formwork for oil storage 02UEK with elev. -1,680 to el. -1.650 according to the executive scheme AKU.1309.02UEK.0.KZ.LB0001- SİNTEK-ABD |  | ЗНО-63435 | 2023-07-11 | 2023-07-12 | 14:30 | 13:28
|  | 02UEK | AKU.1309.02UEK.0.KZ.LB0001 | Бутонирование фундамента склада масел 02UEK с отм. -1,680 до отм. -1,650 | Concreting of the foundation of the oil storage 02UEK with elev. -1,680 to el. -1,650 | + | ЗНО-63436 | 2023-07-11 | 2023-07-12 | 14:30 | 13:29